## Sheet1
Issue | Explanation | Suggestion
Wrong Field in Backup on Delete | In delete_field, when archiving into history, you try to archive from entry_table, but previously already check that count > 0 then reject delete. So in fact, that insert never executed. | Not critical, but if count==0 is enforced, maybe no need to insert dummy into history at all.
dataset_type=corporate | Some placeholders still prepare for corporate, but your code mainly focuses only company_data and compliance. | Either later add corporate support fully, or just keep reserved.
company_template_mapping_form logic | You always DELETE previous company_template_mapping entry before insert. | Which is intended because you maintain only 1 active, but it should be clearly mentioned in docstring (“single active mapping rule”).
pdfkit hardcoded path | wkhtmltopdf path is still hardcoded: C:\\Program Files\\wkhtmltopdf\\bin\\wkhtmltopdf.exe. | It's fine for now, but maybe later you can move to config.py or make environment variable support.

## Sheet2
Status
|  | On Hold | On Going | Dropped | Done | Ready for Test
1 | Penambahan Field Due Date Alert (due_date_alert) pada File Upload |  |  |  | √
2 | Nilai Due Date Alert adalah dalam satuan bulan | √
3 | Nilai Due Date Alert default pada 6 (bulan), dan bisa diubah | √
4 | Alert akan dikirimkan via Email | √
5 | Penambahan table guideline, yang menyimpan link pdf guideline yang bisa di link ke is_sub_header | √
6 | Penambahan Field Is Sub Header (is_sub_header) | √
7 | Is Sub Header (is_sub_header) bisa ditambahkan link ke table guideline | √
8 | Pembuatan Dashboard untuk monitoring Corporate Compliance sheet Completion |  | √
9 | Monitoring terbagi atas 2 tahap |  | √
| Penyelesaian Compliance Sheet per sub header |  | √
| Approval Completion per sub header |  | √
10 | Monitoring meliputi Alert Management |  | √
11 | permintaan server development |  | √
12 | Company Data Editor |  |  |  | √
13 | Start date dan upload date, delete is_copy |  |  |  | √
14 | New table, when editing, the old company_data_entries and compliance_sheet_entries should 'copying' into that table as 'history' for audit before save (update) |  |  |  | √
15 | Upload File + Zip + Encryoted |  |  |  | √
16 | Auto Renumbering Structure |  |  |  | √
17 | Copy template Structure |  |  |  | √
18 | Login Page |  |  |  | √
19 | Forgot Password Page |  |  |  | √
20 | Collapsible / Expandable Structure |  |  |  | √
21 | Convert Ladvo Compliance Sheet |  |  |  | √