## Sheet1
Issue | Explanation | Suggestion
Wrong Field in Backup on Delete | In delete_field, when archiving into history, you try to archive from entry_table, but previously already check that count > 0 then reject delete. So in fact, that insert never executed. | Not critical, but if count==0 is enforced, maybe no need to insert dummy into history at all.
dataset_type=corporate | Some placeholders still prepare for corporate, but your code mainly focuses only company_data and compliance. | Either later add corporate support fully, or just keep reserved.
company_template_mapping_form logic | You always DELETE previous company_template_mapping entry before insert. | Which is intended because you maintain only 1 active, but it should be clearly mentioned in docstring (“single active mapping rule”).
pdfkit hardcoded path | wkhtmltopdf path is still hardcoded: C:\\Program Files\\wkhtmltopdf\\bin\\wkhtmltopdf.exe. | It's fine for now, but maybe later you can move to config.py or make environment variable support.

## Sheet2
1 | Penambahan Field Due Date Alert (due_date_alert) pada File Upload
2 | Nilai Due Date Alert adalah dalam satuan bulan
3 | Nilai Due Date Alert default pada 6 (bulan), dan bisa diubah
4 | Alert akan dikirimkan via Email
5 | Penambahan table guideline, yang menyimpan link pdf guideline yang bisa di link ke is_sub_header
6 | Penambahan Field Is Sub Header (is_sub_header)
7 | Is Sub Header (is_sub_header) bisa ditambahkan link ke table guideline
8 | Pembuatan Dashboard untuk monitoring Corporate Compliance sheet Completion
9 | Monitoring terbagi atas 2 tahap
Penyelesaian Compliance Sheet per sub header
Approval Completion per sub header
10 | Monitoring meliputi Alert Management
permintaan server development
1 | company data editor
2 | Start date dan upload date, delete is_copy
3 | New table, when editing, the old company_data_entries and compliance_sheet_entries should 'copying' into that table as 'history' for audit before save (update)
4 | is it possible for dataset_form_browser changed into tree like ? so it can be collapse or expanded ?
5 | when deleting in dataset_form_browser (company_data_structure and complliance_sheet_structure table), can 'input_code' to be renumbering ? for example i have input_code 1.1.1, 1.1.2, and 1.1.3. if i delete 1.1.2, it will 'renumberig' into 1.1.1 and 1.1.2 (from actualy 1.1.3)
6 | copy compliance sheet